## Sprint Tracking
Story ID | Story Title | Epic | Sprint | Story Points | Status | Priority | Assignee | Role | Label | Start Date | End Date | Days in Progress | Blocked Days | Notes
SMRT-001 | Search apartments by city district | Housing Marketplace | Sprint 1 | 5 | Done | Highest | Anna Berger | Frontend Dev | frontend | 2026-05-04 | 2026-05-08 | 4 | 0
SMRT-002 | Create listing with photos & description | Housing Marketplace | Sprint 1 | 8 | Done | Highest | Markus Hofer | Backend Dev | backend | 2026-05-04 | 2026-05-12 | 8 | 1 | API endpoint refactored mid-sprint
SMRT-003 | Save favorite listings | Housing Marketplace | Sprint 1 | 3 | Done | High | Anna Berger | Frontend Dev | frontend | 2026-05-07 | 2026-05-09 | 2 | 0
SMRT-004 | Filter by price & apartment size | Housing Marketplace | Sprint 1 | 5 | Done | High | Stefan Pichler | Backend Dev | backend | 2026-05-06 | 2026-05-11 | 5 | 0
SMRT-005 | Landlord receives inquiries in-app | Housing Marketplace | Sprint 1 | 5 | Done | Medium | Markus Hofer | Backend Dev | backend | 2026-05-09 | 2026-05-13 | 4 | 0
SMRT-006 | Admin reviews & approves listings | Housing Marketplace | Sprint 1 | 3 | Done | Medium | Stefan Pichler | Backend Dev | backend | 2026-05-10 | 2026-05-13 | 3 | 0
SMRT-007 | Simplified 3-step signup flow | User Onboarding | Sprint 1 | 5 | Done | Highest | Lena Gruber | UX Designer | design | 2026-05-04 | 2026-05-10 | 6 | 0
SMRT-008 | Social login (Google & Apple) | User Onboarding | Sprint 1 | 5 | Done | High | Markus Hofer | Backend Dev | backend | 2026-05-07 | 2026-05-12 | 5 | 2 | Apple developer account delay
SMRT-009 | Welcome tour for new users | User Onboarding | Sprint 1 | 3 | Done | Medium | Lena Gruber | UX Designer | design | 2026-05-09 | 2026-05-12 | 3 | 0
SMRT-010 | Email verification flow | User Onboarding | Sprint 1 | 2 | Done | High | Stefan Pichler | Backend Dev | backend | 2026-05-11 | 2026-05-13 | 2 | 0
SMRT-011 | Stripe integration setup | Payment Integration | Sprint 2 | 8 | Done | Highest | Markus Hofer | Backend Dev | backend | 2026-05-18 | 2026-05-25 | 7 | 2 | Stripe sandbox credentials delayed
SMRT-012 | Secure deposit payment flow | Payment Integration | Sprint 2 | 8 | Done | Highest | Stefan Pichler | Backend Dev | backend | 2026-05-20 | 2026-05-27 | 7 | 0
SMRT-013 | Payment confirmation & receipt emails | Payment Integration | Sprint 2 | 3 | Done | High | Markus Hofer | Backend Dev | backend | 2026-05-24 | 2026-05-27 | 3 | 0
SMRT-014 | Refund processing workflow | Payment Integration | Sprint 2 | 5 | In Progress | Medium | Stefan Pichler | Backend Dev | backend | 2026-05-25 |  | 4 | 0 | Carried to Sprint 3 — edge cases found
SMRT-015 | Payment UI — card input form | Payment Integration | Sprint 2 | 3 | Done | High | Anna Berger | Frontend Dev | frontend | 2026-05-21 | 2026-05-24 | 3 | 0
SMRT-016 | i18n framework setup | Localization | Sprint 2 | 5 | Done | High | Anna Berger | Frontend Dev | frontend | 2026-05-18 | 2026-05-23 | 5 | 0
SMRT-017 | German translation — all UI strings | Localization | Sprint 2 | 5 | Done | High | Lena Gruber | UX Designer | design | 2026-05-21 | 2026-05-26 | 5 | 1 | Freelance translator delivered late
SMRT-018 | Language toggle in settings | Localization | Sprint 2 | 2 | Done | Medium | Anna Berger | Frontend Dev | frontend | 2026-05-24 | 2026-05-26 | 2 | 0
SMRT-019 | Date & currency format localization | Localization | Sprint 2 | 3 | Blocked | Medium | Stefan Pichler | Backend Dev | backend | 2026-05-26 |  | 3 | 3 | Blocked — needs decision on € vs CHF support
SMRT-020 | Legal disclaimers in German | Localization | Sprint 2 | 2 | Done | Low | Thomas Bauer | Marketing | legal | 2026-05-23 | 2026-05-26 | 3 | 0
SMRT-021 | App Store listing (DE & EN) | Launch & Marketing | Sprint 3 | 3 | Done | Highest | Thomas Bauer | Marketing | marketing | 2026-06-01 | 2026-06-04 | 3 | 0
SMRT-022 | Press release for Austrian tech media | Launch & Marketing | Sprint 3 | 2 | Done | High | Thomas Bauer | Marketing | marketing | 2026-06-03 | 2026-06-05 | 2 | 0
SMRT-023 | Social media launch campaign | Launch & Marketing | Sprint 3 | 3 | Done | High | Thomas Bauer | Marketing | marketing | 2026-06-04 | 2026-06-08 | 4 | 0
SMRT-024 | Landing page update for V2.0 | Launch & Marketing | Sprint 3 | 5 | Done | Highest | Anna Berger | Frontend Dev | frontend | 2026-06-01 | 2026-06-06 | 5 | 0
SMRT-025 | Beta tester feedback collection | Launch & Marketing | Sprint 3 | 3 | Done | Medium | Julia Eder | QA Engineer | testing | 2026-06-03 | 2026-06-07 | 4 | 0
SMRT-014b | Refund processing workflow (carried) | Payment Integration | Sprint 3 | 5 | Done | High | Stefan Pichler | Backend Dev | backend | 2026-06-01 | 2026-06-05 | 4 | 0 | Completed after scope reduction
SMRT-019b | Date & currency localization (unblocked) | Localization | Sprint 3 | 3 | Done | Medium | Stefan Pichler | Backend Dev | backend | 2026-06-04 | 2026-06-07 | 3 | 0 | Decision: EUR only for V2.0
SMRT-026 | End-to-end regression testing | Launch & Marketing | Sprint 3 | 8 | Done | Highest | Julia Eder | QA Engineer | testing | 2026-06-01 | 2026-06-09 | 8 | 0
SMRT-027 | Performance load testing | Launch & Marketing | Sprint 3 | 5 | In Progress | High | Julia Eder | QA Engineer | testing | 2026-06-06 |  | 5 | 0 | Ongoing — results pending
SMRT-028 | Go / No-Go launch checklist | Launch & Marketing | Sprint 3 | 2 | To Do | Highest | Lena Gruber | UX Designer | design |  |  | 0 | 0 | Scheduled for sprint end

## Budget Tracking
Month | Category | Planned (€) | Actual (€) | Variance (€) | Variance % | Cumulative Planned (€) | Cumulative Actual (€) | Notes
May 2026 | Development | 15000 | 14200 | 800 | 5.333% | 15000 | 14200 | One dev under-utilized in week 1
May 2026 | UX / Design | 5000 | 5800 | -800 | -16% | 20000 | 20000 | Extra freelance designer for onboarding
May 2026 | QA / Testing | 3000 | 2400 | 600 | 20% | 23000 | 22400 | Testing starts mainly in June
May 2026 | Marketing | 4000 | 3500 | 500 | 12.5% | 27000 | 25900 | Launch campaign prep started
May 2026 | Infrastructure (AWS) | 2000 | 2100 | -100 | -5% | 29000 | 28000 | Staging environment costs higher
May 2026 | Legal / Compliance | 1500 | 1800 | -300 | -20% | 30500 | 29800 | GDPR review for payment data
May 2026 | Contingency | 2000 | 0 | 2000 | 100% | 32500 | 29800 | Not used
June 2026 | Development | 15000 | 16100 | -1100 | -7.333% | 47500 | 45900 | Overtime for payment integration fixes
June 2026 | UX / Design | 5000 | 4200 | 800 | 16% | 52500 | 50100 | Design work front-loaded in May
June 2026 | QA / Testing | 5000 | 5500 | -500 | -10% | 57500 | 55600 | Additional load testing tools
June 2026 | Marketing | 8000 | 7200 | 800 | 10% | 65500 | 62800 | Social media campaign underway
June 2026 | Infrastructure (AWS) | 2500 | 3100 | -600 | -24% | 68000 | 65900 | Production environment scaling
June 2026 | Legal / Compliance | 1000 | 950 | 50 | 5% | 69000 | 66850 | Final review completed
June 2026 | Contingency | 2000 | 1500 | 500 | 25% | 71000 | 68350 | Used for translator rush fee
TOTAL |  | 71000 | 68350 | 2650 | 3.732%
Budget Summary
Total Planned Budget | 71000
Total Actual Spend | 68350
Overall Variance | 2650
Budget Health | Under Budget

## Risk Register
Risk ID | Description | Category | Probability (1-5) | Impact (1-5) | Risk Score | Status | Owner | Mitigation Strategy | Last Updated
R-001 | Stripe integration delays block payment feature | Technical | 4 | 5 | 20 | Active | Markus Hofer | Parallel evaluation of Adyen as backup; weekly sync with Stripe support | 2026-05-20
R-002 | German localization not ready for launch date | Schedule | 3 | 4 | 12 | Mitigated | Lena Gruber | Hired additional freelance translator; reduced scope to core UI strings only | 2026-05-28
R-003 | App Store review rejection delays launch | External | 2 | 5 | 10 | Monitoring | Thomas Bauer | Pre-submission review checklist; TestFlight beta for early feedback | 2026-06-05
R-004 | GDPR compliance gap in payment data handling | Legal | 3 | 5 | 15 | Active | Stefan Pichler | Engaged DPO for audit; Stripe handles PCI compliance natively | 2026-05-22
R-005 | Key developer unavailable during Sprint 3 | Resource | 2 | 4 | 8 | Monitoring | PM (You) | Cross-trained Stefan on Markus's modules; documented all APIs | 2026-05-15
R-006 | Server costs exceed budget due to scaling | Financial | 3 | 3 | 9 | Active | Stefan Pichler | Set AWS cost alerts at 80% threshold; optimize queries before launch | 2026-06-03
R-007 | Competitor launches similar feature first | Strategic | 2 | 3 | 6 | Accepted | Thomas Bauer | Focus on local Salzburg market differentiation; faster iteration cycle | 2026-05-10
R-008 | User adoption below target in first month | Business | 3 | 4 | 12 | Monitoring | Thomas Bauer | Pre-launch email campaign to 2,000 existing users; referral incentive | 2026-06-08
R-009 | Load testing reveals performance bottleneck | Technical | 4 | 4 | 16 | Active | Julia Eder | Running load tests in Sprint 3; database indexing optimization planned | 2026-06-10
R-010 | Currency handling errors (€ formatting) | Technical | 2 | 2 | 4 | Mitigated | Anna Berger | Standardized to EUR-only for V2.0; automated test suite for formatting | 2026-05-30

## Bug Tracker
Bug ID | Title | Related Epic | Severity | Status | Reported By | Assigned To | Date Reported | Date Resolved | Days Open | Sprint Found | Environment
BUG-001 | Payment form crashes on iOS Safari | Payment Integration | Critical | Resolved | Julia Eder | Anna Berger | 2026-05-22 | 2026-05-24 | 2 | Sprint 2 | iOS Safari 17
BUG-002 | Listing photos not loading on slow connections | Housing Marketplace | Major | Resolved | Julia Eder | Markus Hofer | 2026-05-12 | 2026-05-14 | 2 | Sprint 1 | Android Chrome
BUG-003 | German umlauts (ä, ö, ü) break search filter | Localization | Major | Resolved | Lena Gruber | Stefan Pichler | 2026-05-26 | 2026-05-28 | 2 | Sprint 2 | All browsers
BUG-004 | Signup email confirmation link expires too fast | User Onboarding | Minor | Resolved | Thomas Bauer | Markus Hofer | 2026-05-10 | 2026-05-11 | 1 | Sprint 1 | Email clients
BUG-005 | Stripe webhook fails silently on timeout | Payment Integration | Critical | Resolved | Stefan Pichler | Markus Hofer | 2026-05-25 | 2026-05-29 | 4 | Sprint 2 | Production
BUG-006 | Saved favorites count shows wrong number | Housing Marketplace | Minor | Resolved | Julia Eder | Anna Berger | 2026-05-14 | 2026-05-15 | 1 | Sprint 1 | Web app
BUG-007 | € symbol displays as '?' in PDF receipts | Payment Integration | Major | Resolved | Julia Eder | Stefan Pichler | 2026-05-28 | 2026-06-02 | 5 | Sprint 2 | PDF generation
BUG-008 | Language toggle resets after page refresh | Localization | Major | Open | Lena Gruber | Anna Berger | 2026-06-03 |  | -32 | Sprint 3 | Firefox
BUG-009 | Search results page takes >5s to load with 100+ listings | Housing Marketplace | Major | In Progress | Julia Eder | Stefan Pichler | 2026-06-05 |  | -34 | Sprint 3 | Production
BUG-010 | Push notification not sent for new inquiry | Housing Marketplace | Minor | Open | Thomas Bauer | Markus Hofer | 2026-06-08 |  | -37 | Sprint 3 | iOS & Android
BUG-011 | Duplicate listings possible via rapid form submit | Housing Marketplace | Major | In Progress | Julia Eder | Markus Hofer | 2026-06-06 |  | -35 | Sprint 3 | Web app
BUG-012 | Social login button misaligned on small screens | User Onboarding | Minor | Resolved | Lena Gruber | Anna Berger | 2026-05-09 | 2026-05-10 | 1 | Sprint 1 | Mobile 375px
BUG-013 | Refund email sent in English regardless of locale | Payment Integration | Minor | Open | Julia Eder | Stefan Pichler | 2026-06-09 |  | -38 | Sprint 3 | Email
BUG-014 | Admin dashboard timeout on large dataset | Housing Marketplace | Major | In Progress | Julia Eder | Markus Hofer | 2026-06-07 |  | -36 | Sprint 3 | Admin panel
Formulas:
Days Open = TODAY()-[Date Reported]

## Team Summary
Team Member | Role | Sprint 1 Points | Sprint 2 Points | Sprint 3 Points | Total Points | Stories Completed | Bugs Fixed | Avg Days per Story
Anna Berger | Frontend Dev | 8 | 10 | 5 | 23 | 8 | 3 | 3.5
Markus Hofer | Backend Dev | 18 | 19 | 0 | 37 | 8 | 3 | 5.2
Stefan Pichler | Backend Dev | 5 | 10 | 8 | 23 | 7 | 2 | 4
Lena Gruber | UX Designer | 8 | 5 | 2 | 15 | 5 | 0 | 4.5
Julia Eder | QA Engineer | 0 | 0 | 16 | 16 | 3 | 0 | 5.7
Thomas Bauer | Marketing | 0 | 2 | 8 | 10 | 4 | 0 | 3
TEAM TOTAL |  | 39 | 46 | 39 | 124 | 35 | 8 | 25.9

## Burndown Data
Day | Date | Sprint 1 Remaining | Sprint 1 Ideal | Sprint 2 Remaining | Sprint 2 Ideal | Sprint 3 Remaining | Sprint 3 Ideal
1 | 2026-05-04 | 44 | 44
2 | 2026-05-05 | 44 | 39.6
3 | 2026-05-06 | 41 | 35.2
4 | 2026-05-07 | 38 | 30.8
5 | 2026-05-08 | 33 | 26.4
6 | 2026-05-09 | 28 | 22
7 | 2026-05-11 | 20 | 17.6
8 | 2026-05-12 | 12 | 13.2
9 | 2026-05-13 | 7 | 8.8
10 | 2026-05-15 | 0 | 0
1 | 2026-05-18 |  |  | 31 | 31
2 | 2026-05-19 |  |  | 31 | 27.9
3 | 2026-05-20 |  |  | 28 | 24.8
4 | 2026-05-21 |  |  | 23 | 21.7
5 | 2026-05-22 |  |  | 20 | 18.6
6 | 2026-05-23 |  |  | 15 | 15.5
7 | 2026-05-26 |  |  | 12 | 12.4
8 | 2026-05-27 |  |  | 10 | 9.3
9 | 2026-05-28 |  |  | 7 | 6.2
10 | 2026-05-29 |  |  | 5 | 0
1 | 2026-06-01 |  |  |  |  | 34 | 34
2 | 2026-06-02 |  |  |  |  | 34 | 30.6
3 | 2026-06-03 |  |  |  |  | 29 | 27.2
4 | 2026-06-04 |  |  |  |  | 24 | 23.8
5 | 2026-06-05 |  |  |  |  | 19 | 20.4
6 | 2026-06-06 |  |  |  |  | 14 | 17
7 | 2026-06-08 |  |  |  |  | 11 | 13.6
8 | 2026-06-09 |  |  |  |  | 7 | 10.2
9 | 2026-06-10 |  |  |  |  | 5 | 6.8
10 | 2026-06-12 |  |  |  |  | 2 | 0